## Hoja 1
final project timeline
Weeks | 2015-04-29 | [6 empty] | 2015-05-06 | [6 empty] | 2015-05-13 | [6 empty] | 2015-05-20 | [6 empty] | 2015-05-27 | [6 empty] | 2015-06-03 | [6 empty] | 2015-06-10 | [6 empty] | 2015-06-24
days | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Programing and development process | [14 empty] | Code design (Processing & arduino interface) | [6 empty] | Code testing in the test boards
Final 3d Modeling | [14 empty] | Modeling process of the final model in Rhino 3d | [6 empty] | firsts testing of the digital final model | [6 empty] | Final model development | [6 empty] | Latest tests of the digital final model
Prototyping and production | [14 empty] | Start board productions | [6 empty] | Board testing | [6 empty] | Start plywood prototyping - 3d Printing of the Mechanical parts | [6 empty] | Latest plywood prototypes and start of the final production process | [5 empty] | Final productions
General testing & corrections | [41 empty] | Latest testing & corrections
Final object development | [40 empty] | Object development | Final object development | Final presentation
Documentation
Note on B4: ArduinoCode -daniel asprilla
Note on I4: ArduinoCode -daniel asprilla
Note on P4: processing code -daniel asprilla
Note on P5: Rhino 3d Model -daniel asprilla
Note on P6: Board production -daniel asprilla
Note on W4: processing code -daniel asprilla
Note on W5: Rhino 3d Model -daniel asprilla
Note on W6: Board testing -daniel asprilla
Note on AD5: Fianl rhino 3d Model -daniel asprilla
Note on AD6: Prototyping -daniel asprilla
Note on AK5: Testing -daniel asprilla
Note on AK6: Production -daniel asprilla
Note on AP8: Object development -daniel asprilla
Note on AQ6: Production -daniel asprilla
Note on AQ7: Testing & corrections (code, joints etc..) -daniel asprilla
Note on AQ8: Final object development -daniel asprilla
Note on AR8: Final presentation -daniel asprilla