## Gabtt Chart Project Planning
Schedule for Final Project
AquaPonics Pilot System (APPS) |  |  |  |  | Presentation Day | 40 |  |  | Estimated Duration | [5 empty] | Estimated Duration |  |  |  |  | % Completion |  |  |  |  | Beyond Estimated Time | [7 empty] | % Completion (Beyond Estimated Time)
Conception, Construction and Operation | Estimated Start Time | Estimated Duration | Actual Start Time | Actual Duration | Completion | Day
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Design Inspiration | 1 | 3 | 1 | 29 | 100%
2D Design | 27 | 1 | 28 | 1 | 100%
3D Design | 3 | 7 | 3 | 10 | 100%
Additive Fabrication Process | 5 | 10 | 4 | 22 | 100%
Subtractive Fabrication Process | 2 | 7 | 2 | 5 | 100%
Electronics Design and Production | 7 | 14 | 7 | 16 | 100%
Embedded Microcontroller Interfacing And Programming | 14 | 10 | 13 | 22 | 100%
Molding and Casting | 25 | 8 | 26 | 7 | 100%
System Integration and Packaging | 10 | 18 | 7 | 26 | 100%
Future Development | 28 | 5 | 29 | 15 | 50%
Presentation Slide Production | 3 | 33 | 3 |  | 100%
Presentation Video Production | 3 | 33 | 3 | 38 | 100%
Presentation Day | 40 | 1 | 40 | 1 | 100%