## Summary Time Tracker
| Current Date | 2025-04-18
| Final Project Deadline | 2025-06-01
| Number of days left | 44
FINAL PROJECT: STAGES OF COMPLETION
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Week | Weeks Remaining | Concept Finalized | Materials Purchased | Materials Delivered | CAD Completed | Program Ready | Prototype Tested | Fabricated | Finishing (E.g. Sanding Polishing) | Assembled (Assembly,Wiring, Soldering etc) | Final Product Tested and Passed | Other stuff to do in the Week
1 | April 13 - Apr 19 | [10 empty] | Machine Building Assignment Family Dinner (Mum's B'day) Recitation - Fab Ecosystem | bar: FINAL PROJECT: STAGES OF COMPLETION 1 to FINAL PROJECT: STAGES OF COMPLETION 2
2 | April 20 - Apr 26 | [10 empty] | Molding & Casting Assignment First-aid Safety course | bar: FINAL PROJECT: STAGES OF COMPLETION 3
3 | April 27 - May 3 | [10 empty] | Interface and App Programming Assignment | bar: FINAL PROJECT: STAGES OF COMPLETION 4
4 | May 4 - May 10 | [10 empty] | Systems Integration Assignment | bar: FINAL PROJECT: STAGES OF COMPLETION 5 to FINAL PROJECT: STAGES OF COMPLETION 6
5 | May 11 - May 17 | [10 empty] | Recitation - Fab All-in Wildcard Week Assignment | bar: FINAL PROJECT: STAGES OF COMPLETION 7 to FINAL PROJECT: STAGES OF COMPLETION 8
6 | May 18 - May 24 | [10 empty] | Applications & Implications Project Mgmt Assignment | bar: FINAL PROJECT: STAGES OF COMPLETION 9
7 | May 25 - May 31 | [10 empty] | Recitation Start-ups BLSS T1 Invention, IP & Income | bar: FINAL PROJECT: STAGES OF COMPLETION 10
8 | June 1 - June 7 (Buffer and documentation week)

## Task Tracker
| % of Final Project Completed: | 20.31% |  |  | FINAL PROJECT: STAGES OF COMPLETION
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
S/N | Main Assembly | Sub Assembly | Item/Component | Purpose/Description | Concept Finalized | Materials Purchased | Materials Delivered | CAD Completed | Program Ready | Prototype Tested | Fabricated | Finishing (E.g. Sanding Polishing) | Assembled (Assembly,Wiring, Soldering etc) | Final Product Tested and Passed | % Completed
1 | Top Prism | Clock display panel | ESP32 | Microcontroller | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 40%
2 | Top Prism | Clock display panel | ESP32 PCB | To mount the ESP32 and connect to other components | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 40%
3 | Top Prism | Clock display panel | Digit 1 | Number for clock display | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30%
4 | Top Prism | Clock display panel | Digit 2 | Number for clock display | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30%
5 | Top Prism | Clock display panel | Digit 3 | Number for clock display | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30%
6 | Top Prism | Clock display panel | Digit 4 | Number for clock display | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30%
7 | Top Prism | Clock display panel | Dot Dot | Colon for clock display | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30%
8 | Top Prism | Clock display panel | Alarm ON/OFF indicator | LED? Indicator to show if alarm is ON or OFF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
9 | Top Prism | Clock display panel | Alarm Stop Button | To stop Alarm | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
10 | Top Prism | Clock display panel | Bracket - Clock Display Assembly | To mount and hold PCB and clock display elements (e.g. digits) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
11 | Top Prism | Clock display panel | Wooden Frame Panel | Structure | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20%
12 | Top Prism | Clock display panel | Wood Veneer | Protective/aesthetic veneer | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40%
13 | Top Prism | Speakers and testing panel | Speakers (x2) | Produce sound for alarm | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 50%
14 | Top Prism | Speakers and testing panel | MP3 Player | Plays audio | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 50%
15 | Top Prism | Speakers and testing panel | Amplifier Module | Control volume of speakers | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 50%
16 | Top Prism | Speakers and testing panel | Amplifier Module knob - OPTIONAL | Suits the wood theme better | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10%
17 | Top Prism | Speakers and testing panel | Test cycle button | Starts a cycle to test if the components are working properly | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
18 | Top Prism | Speakers and testing panel | Alarm ON/OFF switch | Turns the alarm ON or OFF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
19 | Top Prism | Speakers and testing panel | Wooden Frame Panel | Structure | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10%
20 | Top Prism | Speakers and testing panel | Wood Veneer | Protective/aesthetic veneer | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10%
21 | Top Prism | Speakers and testing panel | Fold-down carrying handle - OPTIONAL | For carrying the clock around | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10%
22 | Top Prism | Prism Core | Prism Core Structure | Structure & battery/power supply housing | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10%
23 | Top Prism | Prism Core | Battery/Power supply | Powers the clock (USB cable?) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
24 | Top Prism | Prism Core | Slide and lock connection | Connects Top Prism to lower body components | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
25 | Bottom Car | Chassis | Top connector plate | Connects to the Top Prism and power unit | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 10%
26 | Bottom Car | Chassis | 6 X Pillars | Structure - Wire channels hidden on inner side of pillars | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 30%
27 | Bottom Car | Chassis | Base plate | To mount the ram and attach the wheel axels | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20%
28 | Bottom Car | Chassis | Solenoid ram | Produces the ramming action | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30%
29 | Bottom Car | Chassis | Wheel axels | Connect wheels to base plate | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 30%
30 | Bottom Car | Chassis | 6 X Wooden Wheels | Battering ram wheels - Aesthetic feature | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 30%
31 | Misc Hardware | Misc | Bolts, screws and fasteners | Joining things together | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
32 | Misc Electronics | Misc | Wires | Connect the various electronic components together | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10%

## BOM
[5 empty] | Dimensions (mm) |  |  | BOUGHT | [5 empty] | USED |  | ORDER STATUS
S/No | Category | Item/Component | Purpose/Description | Source | L (mm) | W (mm) | D (mm) | QTY BOUGHT | Unit Price ($SGD) | Total Price ($SGD) - Without shipping | Shipping ($SGD) | Discounts ($SGD) | Total Price ($SGD) | QTY USED | Total Price ($SGD) | Order Date | Estimated Delivery Date | Delivered on
| Electronics | Seeed XIAO ESP32-C3 | Microcontroller | Provided by Fab Lab | 21.5 | 17.5 | 3 | 1 | 10 | 10 | 0 | 0 | 10 | 1 | 10 | 2025-01-21 | 2025-01-21 | 2025-01-21
| Electronics | FR1 | To mount the ESP32 and connect to other components. FR1 | Provided by Fab Lab | 50 | 75 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2025-01-21 | 2025-01-21 | 2025-01-21
| Electronics | Neopixel LED strip | For clock display digits and dot-dot | [6 empty] | 0 |  |  | 0 |  | #DIV/0!
| Wood | Wood Stock - 10mm thick | Main Material - Pine Solid Wood | Annta Wood | 400 | 195 | 10 | 3 |  |  |  |  | 0 |  | 0
| Wood | Wood Stock - 20mm thick | Main Material - Pine Solid Wood | Annta Wood | 400 | 195 | 20 | 3 |  |  |  |  | 0 |  | 0
| Wood | Wood Veneer | Protective/aesthetic veneer | Shopee - focus.sg | 250 | 60 | 0.5 | 1 | 18.18 | 18.18 | 1.49 | 0 | 19.67 | 1 | 19.67 | 2025-04-01 | 2025-04-07 | 2025-04-07
| Electronics | LED for Alarm ON/OFF indicator | LED? Indicator to show if alarm is ON or OFF | Provided by Fab Lab | 33 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0
| Housing | Bracket - Clock Display Assembly | To mount and hold PCB and clock display elements (e.g. digits). Likely to be a mix of laser cut acrylic and 3D printed elements | Provided by Fab Lab |  |  |  | 1 | 10 | 10 | 0 | 0 | 10 |  | 0
| Electronics | Speakers (x2) | Produce sound for alarm | Provided by Fab Lab |  |  |  | 2 | 5 | 10 | 0 | 0 | 10 | 2 | 10
| Electronics | zwinz1aa UART Control Serial MP3 Music Player Module For AVR ARM PIC | Plays audio | Shopee - zwinz1aa.sg | 43 | 25 | 7 | 3 | 6.71 | 20.13 | 1.49 | 0 | 21.62 | 1 | 7.2067
| Electronics | 5V AM8406 Digital Amplifier Board DIY Small Speaker 5W+5W Dual Channel Stereo Amplification Module | Control volume of speakers | Shopee - walitown.sg | 55.12 | 32.26 | 15 | 2 | 7.68 | 15.36 | 1.49 | 0.77 | 16.08 | 1 | 8.04 | 2025-04-03 | 2025-04-09 | 2025-04-09
| Electronics | Battery/Power supply | Powers the clock (USB cable?) | [6 empty] | 0 |  |  | 0 |  | #DIV/0!
| Electronics | Solenoid ram - 65N, 20mm stroke | Solenoids for driving the ram | Shopee - Kuriosity | 111 | 30 | 38 | 1 | 17.2 | 17.2 | 1.99 | 0 | 19.19 | 1 | 19.19
| Wood | Wooden rod for Wheel axels | Connect wheels to base plate | Daiso | 450 | 9 | 9 | 2 | 2.14 | 4.28 | 0 |  | 4.28 |  | 0 | 2025-04-08 | 2025-04-08 | 2025-04-08
| Hardware | Bolts, screws and fasteners | Joining things together | [6 empty] | 0 |  |  | 0 |  | #DIV/0!
| Electronics | Wires | Connect the various electronic components together | [6 empty] | 0 |  |  | 0 |  | #DIV/0!