## Sheet1
WEEKS
N# | ASSIGMENTS | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | Define a Final project Idea | bar: WEEKS 1 to WEEKS 2
2 | Design Frame version 1 | bar: WEEKS 2 to WEEKS 3
3 | Design 3D parts version 1 | bar: WEEKS 2 to WEEKS 3
4 | Research posible electronic components | bar: WEEKS 4 to WEEKS 5
5 | Research posible costs | bar: WEEKS 4 to WEEKS 5
6 | Research and find controller options | bar: WEEKS 4 to WEEKS 5
7 | List and define the final componets | bar: WEEKS 6 to WEEKS 7
8 | List the materials I will get for the Fab Lab. | bar: WEEKS 6 to WEEKS 7
9 | Design 3D parts version 2 | bar: WEEKS 8 to WEEKS 9
10 | Buy Electronics Components | bar: WEEKS 10 to WEEKS 12
11 | Buy Frame materials | bar: WEEKS 10 to WEEKS 12
12 | Define the Interface to use | bar: WEEKS 13 to WEEKS 14
13 | Design Frame final version | bar: WEEKS 14 to WEEKS 15
14 | Design 3D part final version | bar: WEEKS 14 to WEEKS 15
15 | Produce the parts Frame and 3D parts | bar: WEEKS 16 to WEEKS 17
16 | Test join Parts | bar: WEEKS 17
17 | Add Final Details | bar: WEEKS 17
18 | Final assembly | bar: WEEKS 17
19 | Testing for improvements | bar: WEEKS 17 to WEEKS 18
19 | Final Result and Presentation. | bar: WEEKS 17 to WEEKS 18