## Schedule
Penny Pal
Month | Week | Day/Date | Task | Check list | Remarks
May | Wildcard Week | 16th | Chute mechanism 3D print test | TRUE | Works for 1,2 and 5 rupee coins. The coin chute's inside requires smoothening.
|  | 17th(S) | PCB Design | TRUE | Completed Block Diagram
|  | 18th | Wildcard Production | TRUE | Laser cut metal origami - stainless steel
|  | 19th | Wildcard Documentation | TRUE | Completed
|  | 20th | PCB Mainboard board design | TRUE | Work in Progress
| Applications and implications, project development | 21st | Weekly Assignment Documentation | TRUE | Completed
|  | 22nd | PCB Mainboard board design | TRUE | Completed
|  | 23rd | PCB Breakout board design | TRUE | version 1
|  | 24th(S) | PCB Breakout board design | TRUE | requires changes, revisions - in progress
|  | 25th | PCB production & testing | TRUE | milled breakout board
|  | 26th | Enclosure design | TRUE | Finished soldering breakout PCB. Working on coin collection chamber
|  | 27th | Enclosure design | TRUE | Work in Progress
| Invention, intellectual property, and income | 28th | Enclosure design | TRUE | Work in progress - Not completed
|  | 29th | Weekly Assignment Documentation | TRUE | Completed
|  | 30th | Enclosure Design | TRUE | Ongoing - tested battery snap fit
|  | 31st(S) | Enclosure Design and Tests | TRUE | Testing Annular Snap fir for snout speaker
June |  | 1st | Enclosure Design and Tests | TRUE | Testing Coin acceptor and buttons
|  | 2nd | Enclosure Production | TRUE | Main Shell
|  | 3rd | Enclosure Production | TRUE | Bottom Shell, Snout
| Presentation Week | 4th | Enclosure Production | TRUE | Coin Plate, tail, battery snaps, booster snaps
|  | 5th | Main PCB Production | TRUE | Coin Chute, Integrate Codes and test
|  | 6th | Solder, test | TRUE | Laser Cut and print Tray
|  | 7th(S) | Enclosure Production | TRUE | Assembly
|  | 8th | Integrate Codes and test | TRUE | video production
|  | 9th | Video & Slide | TRUE
|  | 10th | Presentation

## Copy of Schedule (hidden)
Penny Pal
Month | Week | Day/Date | Task | Details | Check list | Status | Remarks
April | 13 | 25th | Schedule | Project Management | Share it with Saheen | Completed | Need to be updated weekly
|  |  | Finalise the component list |  |  | Completed | Discussed, waiting for delivery
|  | 26th | Answer the questions from the Applications & Implications week | https://fabacademy.org/2026/classes/applications_implications/index.html | Add/link it to the final Project page | Completed | Created a new page and linked it to the final project page
| 14 | 29th -1st | Work on the Mobile App for the Project | https://fabacademy.org/2026/classes/interface_application_programming/index.html | Setting a goal, Piggy Bank Savings Tracking, Current total, Last inserted coin. | Completed | Goal setting through app achieved.
May | [6 empty] | App shows follwoing information: Current Total, Percentage (tracking) and Last inserted Coin.
|  | 2nd - 4th | Work on PCB Schematic |  | Verify the schematics with Saheen | Ongoing
| 15 | 6th -11th | Testing | Test Sensor with Servo, button and Neopixel | Isolated tests and integrated (incremental) | Ongoing
|  |  | System Integration | Design it according to PCB and other mechanisms/components | Create a Mock-up, Figure out flap mechanism, Neopixel placement | Ongoing
| 16 | 16th | PCB production |  |  | Not Started
| 17 | 23rd | Finalise Enclosure Design |  |  | Not Started
| 18 | 30th | Integrate Codes and test |  |  | Not Started
June |  | 1st-2nd | Minor corrections, finshes |  |  | Not Started
| 19 | 3rd - 5th | Video and Slide | Video Editting and Slide Design | Check the parameters (duration, resolution, size) | Not Started
|  | 8th - 12th | Presentation

## BOM
Penny Pal
List of components required:
No. | Component | Quantity | Description | Price | Link | source
1 | XIAO ESP32-C6 | 1 | Main controller, WiFi built in | ₹677 | https://robu.in/product/seeed-studio-xiao-esp32c6 | Fab Inventory
2 | IR sensor module | 1 | Object/Coin detection | ₹25 | https://robu.in/product/ir-infrared-obstacle-avoidance-sensor-module?gad_source=1&gad_campaignid=20363337560&gclid=CjwKCAjwwdbPBhBgEiwAxBRA4cce-krDuLHcvBznIENJ7UHYnrKcibliqFqLftlz3Lzj20MqKztfZxoCs9QQAvD_BwE&gbraid=0AAAAADvLFWeWaUmDwn18gNQBuJcOPRmtM | Fab Inventory
3 | Tactile push buttons | 3 | Denominations | ₹13 x 4 | https://robu.in/product/6x6x5-tactile-push-button-switch?gclid=CjwKCAjwwdbPBhBgEiwAxBRA4VT2gI3UMlGgFaCtOpM589XNgmzkE40X3DIVQIoOa7GQVH8-f8orFRoCWi0QAvD_BwE&gad_campaignid=17427802703&gad_source=1&gbraid=0AAAAADvLFWeXbID8fZ_gC7nIsDo-b1Kg- | Fab Inventory
4 | NeoPixel LEDs | 1 | Progress tracking and feedback | ₹490 | https://robu.in/product/1m-ws2812b-5v-addressable-rgb-non-waterproof-led-strip-light-60leds-m?gbraid=0AAAAADvLFWdi_WGXN-JatdM0GRFk85YNL&gad_source=1&gad_campaignid=17416544847&gclid=CjwKCAjwwdbPBhBgEiwAxBRA4cE8isJH8Bx4F4DeJfM8SSBonVpizva6tY8zxNQmbopnJVfQ6z8jmRoCye4QAvD_BwE | Fab Inventory
5 | JQ6500 | 1 | MP3 playback | ₹190 | https://techiesms.com/product/jq6500-mp3-voice-module/?srsltid=AfmBOoob4VyZByBuXKMF6-IFMNzVOz2ZgTvVyJo2RyV0X-AvDWrZpHMo | Fab Inventory
6 | Speaker 0.5W 8Ω | 1 | Snout audio | ₹28 | https://robu.in/product/0-5w-8ohm-trumpet-speaker-diameter-28mm | Fab Inventory
7 | Micro Solenoid | 2 | Lock mechanism - DC5V Solenoid Push-Pull Linear Actuator Motor Electromagnet Mini | ₹499 | https://probots.co.in/dc5v-solenoid-push-pull-linear-actuator-motor-electromagnet-mini.html | Purchased
8 | Decoupling capacitors | 2 | Power stability | ₹ | https://inventory.fablabkerala.in/ | Fab Inventory
9 | JST connectors | ? | Module connections | ₹ | https://inventory.fablabkerala.in/ | Fab Inventory
10 | Battery | 1 | Li - ion battery | ₹107 | https://inventory.fablabkerala.in/ | Fab Inventory
11 | Booster | 1 | for battery | ₹ | https://inventory.fablabkerala.in/ | Fab Inventory
12 | PLA | 1 | for 3D printing the enclosre and supporting structures | ₹ | https://inventory.fablabkerala.in/ | Fab Inventory
13 | Acrylic Sheet | 1 | for Laser cutting | ₹ | https://inventory.fablabkerala.in/ | Fab Inventory
14 | FR1 PCB material | 1 | PCB production | ₹ | https://inventory.fablabkerala.in/ | Fab Inventory

## Gantt Chart
Penny Pal
| PROJECT TITLE |  | SMART PIGGY
| Project Manager |  | MISHAEL
| WBS NUMBER | TASK TITLE | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
| 1 | Project Conception and Initiation
| 1.1 | Brainstorming | 2026-04-25 | 2026-04-25 | 0 | 100%
| 1.2 | Project Planning | 2026-04-25 | 2026-04-26 | 1 | 100%
| 1.3 | Research | 2026-04-25 | 2026-05-10 | 15 | 100%
| 1.4 | Prepare BOM | 2026-04-30 | 2026-05-02 | 2 | 100%
| 2 | Electronics and Programming
| 2.1 | Block Diagram | 2026-05-06 | 2026-05-07 | 1 | 100%
| 2.2 | PCB Design | 2026-05-07 | 2026-05-14 | 7 | 100%
| 2.3 | PCB Production | 2026-05-15 | 2026-05-16 | 1 | 100%
| 2.4 | Programming | 2026-05-13 | 2026-05-18 | 5 | 100%
| 2.5 | App Integration | 2026-05-06 | 2026-05-26 | 20 | 100%
| 3 | Design and Production
| 3.1 | Coin Insert Mechanism | 2026-05-07 | 2026-05-08 | 1 | 100%
| 3.2 | Component Placement | 2026-05-08 | 2026-05-11 | 3 | 100%
| 3.3 | Mock Assembly | 2026-05-12 | 2026-05-17 | 5 | 100%
| 3.4 | 3D Printing | 2026-05-28 | 2026-06-05 | 7 | 100%
| 3.5 | Post-Processing | 2026-06-02 | 2026-06-06 | 4 | 100%
| 3.6 | Assembly | 2026-06-06 | 2026-06-09 | 3 | 100%
| 4 | Presentation
| 4.1 | Documentation | 2026-06-05 | 2026-06-08 | 3 | 100%
| 4.2 | Video Scripting | 2026-06-03 | 2026-06-05 | 2 | 100%
| 4.3 | Slide | 2026-06-03 | 2026-06-05 | 2 | 100%
| 4.4 | Video Recording | 2026-05-18 | 2026-06-01 | 13 | 100%
| 4.5 | Video Editing | 2026-06-03 | 2026-06-05 | 2 | 100%

## User Flow
Parent App |  | Firebase |  | XIAO ESP32 C6 |  | Hardware
Parent sets goal | ⏩ | Goal stored | ⏩ | Goal recieved | ⏩ | Servo 1 locks
Kodular app |  | goal amount field |  | Wi-Fi - Firebase |  | Flap closed - Piggy locked
|  | Coin insertion event |  | IR interrupt fired | ⏪ | IR beam broken
|  |  |  | Awaits denomination |  | Coin detected - digital low
⏬
|  |  |  | Play "Hello" |  | Speaker plays
|  |  |  | Trigger Audio Feedback |  | "Hello" audio track
|  | Denomination selection |  | Coin value read | ⏪ | Button Presed
|  |  |  | Map GPIO > rupee |  | 1/2/5/10 rupee
|  |  |  | Update total + % |  | Read Coin Selection Input
↘️
Servo 2 opens flap
Coin drops into bank
Servo 2 closes flap
Data sync to Firebase and app
App refreshes | ⏪ | Firebase updates | ⏪ | XIAO writes to DB
Total saved |  | Total saved |  | Total saved
Progress Bar |  | last coin |  | last coin
Last coin value |  | percentage % |  | percentage %
|  |  |  | Check progress % | Yes⏩ | Play "Yayyy!"
|  | Audio feedback logic |  | 25/50/75/100 |  | Celebratory track
|  |  |  | milestone reached? |  | Neopixel changes colour
|  |  |  | ⏬ No |  | red to orange to yellow to green (gradual)
Play "Thank you"
|  |  |  | Acknowledgement track |  | Speaker outputs audio
|  |  |  | total = goal? | Yes⏩ | Servo 1 unlocks
|  |  |  | Check on every insert |  | Piggy bank opens
|  |  |  | ⏬ |  | ⏬
App notifies parent | ⏪ | Firebase pushes | ⏪ | Write goal achieved |  | Neopixel celebration
Goal reached! |  | goal achieved = true |  | true > Firebase |  | Rainbow/full strip